## PDSAForm
Date Initiated | Main Staff Contact | PDSA Cycle | We plan to | We hope this produces | Steps to execute | What did you observe? | Did you meet your measurement goal? | What did you conclude from this cycle? | Next Action Step
<<<<<<<<<< | See list of Tactical Items for corresponding Item #
| Del | TA 01: Create an MCN Development plan
2013-01-25 | Del | 01: Create an MCN Development Plan | Invite the Board of Directors to submit sample development plans. | several plans to guide us as we move forward with the Board to develop and finalize a plan. | Send Board e-mail re submitting sample development plans. | One board member sent a sample plan
2013-01-25 | Del | 01: Create an MCN Development Plan (Karen, Lead; Del; Charlotte) | Google Development Plans and each identify our favorite template or table of contents. We will share these with each other and on Monday January 28th Del and Charlotte will present our findings at the staff meeting. | an understanding of where we are going with this goal and what the plan will cover when it is complete. | 1. Individual research on line. 2. Share favorite plan templates with each other. 3. Review each other’s submissions. 4. vote to select the best model for our plan 5. Share with staff. | 1. We did not find a ready-made organizational development plan on which to model ours. 2. We need more time to share plans and obtain feedback. | We did not. | We need to schedule time to discuss Karen's documents before presenting to staff. Del proposed to skype with Beatriz Perez regarding this development plan goal. | Del will set up skype meeting with Beatriz.
| Del | 01: dicuss operational plan with Beatriz Perez | Investigate ways to link operational plan to overall development plan | an annual operational plan that fully takes into account the development plan | conduct initial telephone conversation report outcomes of monday morning Eric call to Beatriz schedule follow up call
| Charlotte | TA 03: Apply to 5 new foundations
2013-02-13 | Jennie | 03: Apply to 5 new foundations | Consider PCORI application | partnership with MacColl and grant funding | Meet with Michael Parchman and email staff about PCORI opportunities | Michael and MCN energized to apply June 15 for LOI for Aspect 5 of PCORI | yes | MCN and MacColl to partner on PCORI app
2013-02-01 | Jennie | 03: apply to five new foundations | apply to ITHS with LOI | full application request | write LOI and get support letter from PNWU | LOI submitted | yes |  | wait for results of LOI
2013-02-13 | Jennie | 03: Apply to five new foundations | LOI accepted from ITHS! | full apllication | Partner with Michael Parchman, meet with Leo Morales, write application outline | Full application submitted March 15 | yes |  | wait for results for application
TA 04: Develop an Advocacy Agenda
2013-01-29 | Adrian | 04: Develop an advocacy agenda | Have first meeting week of 1/28/13 | Understanding of tactical action and identifying key members for next meeting | 1) Email interested members 2) Propose meeting times using Doodle 3) Decide on first meeting | Doodle does not work to reach members to coordinate meeting times | No | After two doodle attemps, we need to find a more effective communication route to get those involved communicating about the subject. Time was wasted trying to schedule a phone call because of peoples differing schedules.
2013-02-06 | Adrian | 04: Develop an Advocacy Agenda | Test use of Smartsheet discussion as mechanism for initial conversation | Clarity around tactical action and next steps. | 1. Begin Smartsheet Discussion 2. Notify staff members of Discussion 3. Set smart sheet reminders 4. Evaluate by 2/13 | Observed that smartsheet was a very organized and effective communication method. Received input and response from all but 1 member. | Yes | That smartsheets are the most effective route for communicating between MCN staff for different reasons. 1) documenting communication from staff 2) centralized communication arena and 3) reminders to add to conversation.
2013-02-21 | Adrian | 04: Develop an Advocacy Agenda | Meet with Michael to discuss Advocacy Agenda's provided and decide on next action step | First step in Developing an Action Plan including discussion items for meeting with appropriate staff. | 1. phone call to MP 2. deciding on effective way to generate first guided discussion | Ways to set a guided discussion | Yes
2013-02-26 | Adrian | 04: Develop an Advocacy Agenda | Set Round Table Discussion | 1) Staff understanding on Advocacy Agenda 2) Identified issues to focus on for the MCN advocacy agenda 3) Next steps | 1) Contact key staff for availabilty 2) Email interested members on the date and time for Round Table Discussion 2) Set date if 90% of "interested members" can attend. 3) Set discussion. | Staff Very Responsive. Date set | Yes
2013-02-26 | Adrian | 04: Develop an Advocacy Agenda | Create a smart sheet for this topic that lets staff view, review, edit, input Advocacy Items. | 1) Centralized venue for Advocacy Communication | 1) Create Smartsheet 2) Email all staff to identify interested members 3) Add thos staff to this smart sheet | Everyone on staff with one exception was on board with this smartsheet and has contributed | Yes
2013-02-26 | Adrian | 04: Develop an Advocacy Agenda | Identify an important advocacy item per staff member | A list to present to the Round Table Discussion for the "interested" staff members on 2/26/13 | 1) Contact each staff member individually 2) Ask them for them to identify ONE key advocacy item important to them 3) Create a list for Discussion | When allowed to sit and think on it, they pushed the topic aside and very few responded. When asked for a response and a follow up reminder. I got more responses | Yes
2013-02-26 | Adrian | 04: Develop an Advocacy Agenda | Identify important advocacy items per Board Member | A list to present to the Round Table Discussion | 1) email each board member individually 2) create list | 7 of 8 board members responded | Yes
2013-02-26 | Adrian | 04: Develop an Advocacy Agenda | Identify advocacy issues that MCN is already involved in | A list for the Round Table Discussion | 1) email group on Thursday to think about this 2) Ask Jillian to include in Monday Staff Call 3) Document the list | We have a few advocacy efforts that are clearly listed. | Yes
2013-03-18 | Mike | 04: Develop an Advocacy Agenda | Share process for developing advocacy agenda content; Clarify with Karen about how to respond to media requests and proceed with advocacy efforts | Increased knowledge among staff about how we are developing the advocacy agenda; Clarity from Karen about how to proceed with advocacy activities. | 1. Share a recap of conversation surrounding the advocacy agenda and issues identified: Immigration Reform and Access to Care. 2. Solicit a response from Karen about how to proceed with specific advocacy activities.
2013-03-28 | Adrian | 04: Develop an Advocacy Agenda | Contact staff listed in the notes to identify next steps in drafting the agenda | A plan to draft the agenda | 1) read notes from Staff Discussion 2) send email to staff members identified in notes 3) ask for a date they plan on having a discussion.
| Jillian | TA 10: Staff Meeting Redesign
2013-02-11 | Jillian | 10 Staff Meeting Redesign | Revise guiding/discussion questions for the check-in process | More targeted discussion around needs to be addressed | Jillian issues revised questions for 2/11 staff meeting
2013-01-28 | Jillian | 10: Staff Meeting Reengineering | Move the time of staff meetings to 1pm CST | More thoughtful and organized discussions and presentations by staff during the staff meeting. | Propose a new time, get feedback and set it up on the calendar for the January 28th staff meeting. | Staff seemed to be more engaged, aware of time and prepared to present | We did not set a measurement goal, but 90% of staff surveyed felt the new time was an improvement | The later time is an improvement and we will continue with the later time for subsequent staff meetings | There is still work to be done to further improve the staff meeting
2013-02-01 | Jillian | 10: Staff Meeting Rengineering | Introduce a set of questions to guide the check-in process | More thoughtful and organized discussions and presentations by staff during the staff meeting. | 1. Send an email with proposed guiding questions 2. Test drive questions at Monday's staff meeting | Questions seemed to give more structure to the check-ins. 100% of staff answering the survey felt it was an improvement, but that there needed to be some changes. | Yes | Questions are helpful, but need some tweaking | Revised questions for next staff meeting
| Jessica | 12: Find funding for women's health programs
2013-03-13 | Becca | 12: Send potential womens health funding opportunity to TA team | Send potential funding opportunity for women's health out to folks interested in the TA | Produces engagement from the team regarding a potential opportunity; Determine if there is interest in the opportunity or not | Becca to email link to the funding page out to team members
TA 20: Determine how / if to provide junior staff with access to learn from clinics; professional development in the field
2013-02-18 | Becca | 20: Confirming travel plans with Joan Combellick | Email Joan and establish what days and times Becca will be traveling up state to visit her | Set plans for out of state travel | Review past emails with Joan, email her again, and see what follow up contact needs to be made prior to March 1 | Joan emails back promptly and welcoming | Yes | Becca will be in New Paltz/Beacon with Joan on March 6 & 7 | Go to NYC!
| Jennie | TA 22: Develop more formal intern program for MCN.
2013-02-11 | Theressa | 22: Formal intern process | Send out email to two orgs who previously showed interest in supporting interns | a request to interview intern | 1. Send initial email describing intern and asking if interested | no response from either org | no | either email or email message was not sufficient to elicite a response | call on the phone, if placement still needed, will check with Jennie
2013-02-01 | Becca/Jennie | 22: Formal intern program | Create a smartsheet to track all intern contacts and placements | organizational clarity | Becca set up smartsheet. Jennie test. others test. | Becca and Jennie agreed on sheet. |  | need to spread to staff | staff informed of intern spreadsheet
2013-02-11 | Jennie | 22: Intern communication | add Theressa's summary as an attachment | more resource information | ask Theressa to add
2013-02-11 | Jennie | 22: Intern communication | Michael to enter Salibury office interns | more complete entries | ask Micahel again | stated they couldn't do it until Feb 18 | No | delays are probable if it isn't a priority for staff who are needed | get commitment from staff to process. Discuss with Karen and Eric
2013-02-18 | Jennie/Becca | 22: Intern communication | call Kerry to complete PDSA with MD | completion of info | ask Becca to email or call Kerry this week | MD office wanted to fill out sheets on 2/18 | no | difficulty in communication and collaboration | change form to "email contact"instead of contact. Continue
| Jennie | TA 23: Find creative ways to engage with clinicians (contest, etc.)
2013-02-06 | Jennie | 23: Clinician Engagement | Host a gathering at Western Forum to assess clinical issues and network | networking, increased knowledge of MCN, learning by staff of clinician needs, possibilities for future work | Contact Seth about a meeting spot; secure spot; publicize meeting by getting list of registrants |  |  |  | hold meeting: meeting held with 14 attendees! Successful
2013-02-13 | Jennie | 23: Clinician engagement | Establish Card Study | Sentinel Network of MCN clinicians | learn about method, pick topic, find partners
2013-02-28 | JM | 23: Clinician engagement at Forum | follow up with clinicians from Forum | participating clinician members | email all attendees and ask if they want to be on MCN mailings; ask them what their biggest issues are; ask if any want to be in Card studies | quick responses to emails but difficult to get concrete next steps from individuals. Enthusiastic but need a concrete task | partially | need to be concretely giving or getting responses to clinicians so the engagement is real and momentum continues | email twin physicians about card study
TA 24: Communications strategy
2013-01-25 | Jennie | 24: communication | clarity and accuracy in emails by matching subject line to content | improve efficiency and accuracy in communication | 1. emailed all staff asking them to put subject line in emails that corresponds to content.If replying, and subject changes then change subject line before submitting reply. Test for one week | much better although unclear if sustained | yes | continue another week or two of measure | observe another couple of weeks: it's good!
| Theressa | TA 50: Create a functional manual for the TA Navigator
2013-01-29 | Theressa | 50: Step 1-a Feedback on usability (Charlottee) | Test the use of the manual | Feedback on real-time issues encountered with the training manual so corrections and helpful additions can be may be made before it is instituted | 1.Hold a training session on the TA navigator with Charlotte 2.Give Charlotte the TA Navigator Draft Manual as a back up to assist with entering TA 3.Hold a second feedback session with Charlotte a week later regarding the manual and suggested changes, etc. | This PDSA has been delayed by one week due to problems with the database not matching the manual | No | continue another week | observe another week
2013-02-18 | Theressa | 50: Step 2-aFeedback on usuability (Charlotte) | Test the use of the manual | Feedback on real-time issues encountered with the training manual so corrections and helpful additions can be may be made before it is instituted | 1. Give Charlotte more time to use the manual with the updated TA navigator 2. Request feeback on usability | Charlotte gave feedback in the form of handwritten edits and suggestions to the draft document. | Yes | Additional time allowed Charlotte to give the needed feedback | Review feedback and incorporate necessary changes
2013-02-25 | Theressa | 50: Step 1-b Feedback on usability (Kerry) | Test the use of the manual | Feedback on real-time issues encountered with the training manual so corrections and helpful additions can be may be made before it is instituted | 1.Hold a training session on the TA navigator with Kerry 2.Give Kerry the TA Navigator Draft Manual as a back up to assist with entering TA 3.Hold a second feedback session with Kerry a week later regarding the manual and suggested changes, etc. | Kerry gave feedback in the form of an emial | Yes | this cycle took longer than the usual 1 week, however, given that Kerry works part-time I think the response time was appropriate in this instance and provided for a sucessful PDSA | Review feedback and implement necessary changes, re-test the TA manual
2013-02-13 | ER/BP/JM/KM | 51: Reinforce Process at Monday Morning Meetings | Incorporate a more effective update regarding this process at our next Monday morning meeting | More clarity and confidence regarding the new PDSA process | 1. Karen, Jennie, and/or Becca to solicit stories of PDSA successes and failures thus far -- and celebrate all 2. Becca to share the PDSA form and the attached Excel-based tracking sheet 3. Solicit feedback at meeting | At last discussion, most people had not tried PDSAs so did not have much to comment on | Not particularly | Need further discussion on PDSA, further guidance as well | Meet on March 11 with Eric to further discuss PDSA process
2013-01-31 | Eric/Becca/Jennie | 51: Set up PDSA tracking sheet | Set up a tracking sheet for all of MCN's Tactical Action PDSA cycles | Support and clarity for all of the staff regarding MCN's new PDSA process. | 1. Jennie, Becca, Karen, and Eric to talk via conference call. 2. Becca, with guidance from Jennie, creates a draft form and tracking form on Smartsheets 3. Becca reviews this form with all of the staff at a Monday staff meeting 4. All of the staff review at monthly all-staff call with Eric on February 4 | 1. Need a sorting method for tactical headings 2. different levels of comfort with PDSA 3. incomplete entries by staff on ongoing PDSAs 4. Form is user friendly 5. Hardest part is simply institutionalizing the use of the form 6. Enthusiasm regarding PDSAs; need to celebrate successes and challenges 7. | Yes | We're off to a good start and we need to continue refining | See next PDSA...
2013-02-13 | ER/BP/JM/KM | 51: Strengthen Tracking of PDSAs | Create an ongoing system of sorting the PDSAs on this PDSA form AND tracking the PDSAs initiated on the attached spreadsheet | More clarity regarding where we stand regarding progress on the tactical actions | Becca to set up a weekly system to update the PDSA tracking spreadsheet and sort this PDSA form | 1. Sorting is simple - right click the PDSACycle Column heading, click sort. Sort Ascending; 2. Updating the tracking spreadsheet takes a little more time - have to create and save an entire separate spreadsheet because the one uploaded cannot be edited (it opens in Read Only format). But it is not difficult at all. However, I'm not sure how much this tool will be used. We'll see as it goes on! :) | Yes | Sorting is simple, it just needs to happen periodically. Uploading a new, updated tracking sheet every time is simple and if the tool proves to be useful, then it will be well worth the short amount of time it takes to create | Do the same process again next week. Watch how many PDSAs are being entered in a week. Monitor the usefulness of sorting and tracking.

## Discussions
Row 33 | Discussion Title | 22: Intern communication | aliebman@migrantclinician.org | 02/16/13 8:17 AM
| Comments | Only feedback from Michael is to change contact info to email contact. Will do that. Would be helpful to know how long it took him to enter data. Asked him to time it, but haven't heard that yet. Continue with intern spreadsheet and revise as indicated. | jmclaurin@migrantclinician.org | 02/28/13 7:55 PM
|  | We kindly requested on at least three occasions to give us until 2/18 to populate the spread sheet. The spread sheet was updated with some thoughtful ideas and questions about the spread sheet on 2/18. So from our end, the study part of the PDSA suggests that we need some flexibility with the process. That’s all. We don't at all consider that we were resistant. Instead, we would like celebrate this as thoroughly taking part in the study part of the PDSA. Of course, I am happy to agree to disagree as well. | aliebman@migrantclinician.org | 02/19/13 10:19 AM
|  | I don't think this PDSA demonstrates anything that it actually part of this particular PDSA except resistance to the process. More time (much more) has been spent deciding not to fill in a few rows than to just take the next step.The process will be stopped cold if every PDSA needs to be agreed upon by every participant. The tactical action was agreed upon and this is the process. The next PDSA will be to call Kerry and get the simple information.If the PDSA were a challlenge it would be that the information were difficult to get, or the grid couldn't be filed out, or that filling it took a very long time. Becca and I piloted the grid and it took us less than five miutes to enter a person.Nothing unreasonable was requested. We will move on as best we can whether or not the MD office completes the grid. | jmclaurin@migrantclinician.org | 02/18/13 10:15 AM
|  | This is an excellent PDSA to demonstrate challenges that we need to address with our new strategic approach that is simultaneously incorporating multiple efforts and multiple PDSA cycles. This particular PDSA highlights the need to address and evaluate the week timeframe for all of our PDSAs. A week may not always be feasible and the PDSA literature does not necessarily mandate a week time frame. That said we do want to be fast and nimble -- "see what we can do by Tuesday" but it may not always work that way. This PDSA also demonstrates the need to engage or communicate with desired collaborators prior to undertaking a PDSA. Perhaps with improved communication feasible time frames can be better established and collaborators can feel more engaged with the process. | aliebman@migrantclinician.org | 02/16/13 8:17 AM
Sheet | Discussion Title | Why Email Interested Men? | kmountain@migrantclinician.org | 02/07/13 8:44 AM
| Comments | Yes. Becca is correct. It is not solely IPV. I am working on getting an initial discussion with interested MCN staff members. | avelasquez@migrantclinician.org | 02/08/13 10:27 AM
|  | I think you're referring to the Steps to Execute field on row 4, for the Advocacy Agenda PDSA. If you hover your mouse over the field, it will display all of the text in the cell. It actually says "1.Email interested members 2) Propose meeting times using Doodle 3) Decide on first meeting" The words simply got cut off, as in an Excel sheet. | bpride@migrantclinician.org | 02/08/13 10:13 AM
|  | My understanding is that this is MCN's Advocacy Agenda and that it will be very broad in scope. So it is not just about IPV so I don't understand the involvement of folks outside of MCN, Can you help me with your thinking | kmountain@migrantclinician.org | 02/07/13 8:44 AM